## Summary by SOC on 11-13-2020
| Permit | Schedule of compliance from MDNR | Parameter | Parameter | Design Flow | Type of treatment | Approximate year of construction | Cost Estimate | Capital Improvement Plan Year
1 | Rocky Fork | 2022-02-01 | Ammonia |  | 460000 | Oxidation Ditch | 2014 | 9200000
2 | Midway Arms | 2024-09-01 | Ammonia |  | 4800 | Recirculating sand filter | 2009 | 724150 | 2023
3 | Rollingwood | 2025-11-01 | Ammonia | E. coli | 10000 | Extended aeration WWTP | 1968 | 498100 | 2024
4 | Highfield Acres | 2025-11-01 | Ammonia | E. coli | 29000 | Lagoon | 1968 | 259265 | 2024
5 | Richardson Acres | 2028-11-01 | Ammonia | E. coli | 8510 | Lagoon | 1989 | * | 2024
6 | Brown Station | 2028-11-01 | Lower ammonia | E. coli | 1850 | Recirculating sand filter | 2009 | 1518000 | 2024
7 | South Route K | 2029-11-01 | Ammonia | E. coli | 244000 | Extended air WWTP / Lagoon | 2000 / 1969 | 6454000 | 2027
8 | Trails West | 2031-11-01 | Ammonia | E. coli | 57500 | Lagoon | 1970 | 1122243 | 2029
9 | Twin Lakes | 2032-11-01 | Ammonia |  | 19400 | Lagoon | 1972 | 1169000 | 2030
10 | Cedar Gate | 2034-11-01 | Ammonia | E. coli | 11100 | Lagoon | 1971 | 469287 | 2032
11 | Brookfield Estates | 2035-11-01 | Ammonia | E. coli | 10500 | Recirculating sand filter | 2001 | 1307050 | 2033
12 | Quarter Mile Hills | 2037-11-01 | Ammonia | E. coli | 5480 | Lagoon | 2001 | 102344 | 2036
13 | Sunnyslope | 2038-11-01 | Ammonia | E. coli | 5500 | Lagoon | 1971 | 141000 | 2037
14 | Kinkade Crossing | NA |  |  | 50000 | Extended aeration WWTP | 2007 | 381400 | 2034
15 | Meadow Village | NA |  |  | 16500 | Extended aeration WWTP | 2009 | 620000 | 2031
16 | Midway Crossing | NA |  |  | 150000 | Extended aeration WWTP | 2008 | 2225518 | 2023
16 | Prairie Meadows | NA |  |  | 80000 | Extended aeration WWTP | 2004 - 2006 | 3057000 | 2028
[7 empty] | TOTAL: | 29248357
* Brown Station / Richardson Acres combined cost estimate is $1,518,000
** Cost estimates from "User Rate Study 2019 Schedule of Capital Improvement Plan to 2036"
American Outdoor Brands permit expiration: 2023
Eagle Knoll permit expiration: 2023

## Summary by SOC on 11-6-2020
| Permit | Schedule of compliance from MDNR | Parameter | Parameter | Design Flow | Type of treatment | Approximate year of construction | Cost Estimate | Capital Improvement Plan Year | Deadline for comment | Operational monitoring | Cost analysis for compliance (CAFCOM) | Pounds per day
1 | Midway Arms | 2024-09-01 | Ammonia |  | 4800 | Recirculating sand filter | 2009 | 724150 | 2023 | 2020-10-05 | no | no | 1.2/1.2
2 | Rollingwood | 2025-11-01 | Ammonia | E. coli | 10000 | Extended aeration WWTP | 1968 | 498100 | 2024 | 2020-10-05 | no | no | NA
3 | Highfield Acres | 2025-11-01 | Ammonia | E. coli | 29000 | Lagoon | 1968 | 259265 | 2024 | 2020-10-05 | no | no | NA
4 | Richardson Acres | 2028-11-01 | Ammonia | E. coli | 8510 | Lagoon | 1989 | * | 2024 | 2020-10-05 | no | no | 2.4/3.8
3 | Brown Station | 2028-11-01 | Lower ammonia | E. coli | 1850 | Recirculating sand filter | 2009 | 1518000 | 2024 | 2020-10-05 | no | no | 0.5/0.5
6 | South Route K | 2029-11-01 | Ammonia | E. coli | 244000 | Extended air WWTP / Lagoon | 2000 / 1969 | 6454000 | 2027 | 2020-10-05 | yes | yes | NA
7 | Trails West | 2031-11-01 | Ammonia | E. coli | 57500 | Lagoon | 1970 | 1122243 | 2029 | 2020-10-05 | yes | yes | NA
8 | Twin Lakes | 2032-11-01 | Ammonia |  | 19400 | Lagoon | 1972 | 1169000 | 2030 | 2020-10-05 | no | yes | 7.3/13.0
9 | Cedar Gate | 2034-11-01 | Ammonia | E. coli | 11100 | Lagoon | 1971 | 469287 | 2032 | 2020-10-05 | no | yes | NA
10 | Brookfield Estates | 2035-11-01 | Ammonia | E. coli | 10500 | Recirculating sand filter | 2001 | 1307050 | 2033 | 2020-10-05 | no | yes | 3.2/3.2
11 | Quarter Mile Hills | 2037-11-01 | Ammonia | E. coli | 5480 | Lagoon | 2001 | 102344 | 2036 | 2020-10-05 | no | yes | 1.9/3.2
12 | Sunnyslope | 2038-11-01 | Ammonia | E. coli | 5500 | Lagoon | 1971 | 141000 | 2037 | 2020-10-05 | no | yes | NA
13 | Kinkade Crossing | NA |  |  | 50000 | Extended aeration WWTP | 2007 | 381400 | 2034 | 2020-10-05 | yes | no | NA
14 | Meadow Village | NA |  |  | 16500 | Extended aeration WWTP | 2009 | 620000 | 2031 | 2020-10-05 | no | no | NA
15 | Midway Crossing | NA |  |  | 150000 | Extended aeration WWTP | 2008 | 2225518 | 2023 | 2020-10-05 | yes | yes | NA
16 | Prairie Meadows | NA |  |  | 80000 | Extended aeration WWTP | 2004 - 2006 | 3057000 | 2028 | 2020-10-05 | yes | no | NA
[7 empty] | TOTAL: | 20048357
* Brown Station / Richardson Acres combined cost estimate is $1,518,000
** Cost estimates from "User Rate Study 2019 Schedule of Capital Improvement Plan to 2036"
American Outdoor Brands permit expiration: 2023
Eagle Knoll permit expiration: 2023

## By compliance schedule
| Proposed Permit | Schedule of compliance from MDNR | Parameter | Parameter | Design Flow | Type of treatment | Approximate year of construction | Cost Estimate | Capital Improvement Plan Year | Deadline for comment | Operational monitoring | Cost analysis for compliance (CAFCOM) | Pounds per day
1 | Rocky Fork | 1 year | Lower ammonia |  | 460000 | Oxidation ditch | 2013 | Not applicable (NA) | NA | October 12,2020 | yes | yes | NA
2 | Rocheport |  |  |  | 34400 | Extended aeration WWTP | 1980 | NA | NA | October 12,2020 | yes | no | NA
3 | Sunnyslope | 4 years | Ammonia | E. coli | 5500 | Lagoon | 1971 | 141000 | 2021 | 2020-10-05 | no | yes | NA
4 | Midway Arms | 2024-09-01 | Ammonia |  | 4800 | Recirculating sand filter | 2009 | 724150 | 2023 | 2020-10-05 | no | no | 1.2/1.2
5 | Brown Station | 2025-11-01 | Lower ammonia | E. coli | 1850 | Recirculating sand filter | 2009 | 1518000 | 2024 | 2020-10-05 | no | no | 0.5/0.5
6 | Highfield Acres | 2025-11-01 | Ammonia | E. coli | 29000 | Lagoon | 1968 | 259265 | 2024 | 2020-10-05 | no | no | NA
7 | Richardson Acres | 2025-11-01 | Ammonia | E. coli | 8510 | Lagoon | 1989 | * | 2024 | 2020-10-05 | no | no | 2.4/3.8
8 | Rollingwood | 2025-11-01 | Ammonia | E. coli | 10000 | Extended aeration WWTP | 1968 | 498100 | 2024 | 2020-10-05 | no | no | NA
9 | South Route K | 9 years | Ammonia | E. coli | 244000 | Extended air WWTP / Lagoon | 2000 / 1969 | 6454000 | 2027 | 2020-10-05 | yes | yes | NA
10 | Trails West | 11 years | Ammonia | E. coli | 57500 | Lagoon | 1970 | 1122243 | 2029 | 2020-10-05 | yes | yes | NA
11 | Twin Lakes | 12 years | Ammonia |  | 19400 | Lagoon | 1972 | 1169000 | 2030 | 2020-10-05 | no | yes | 7.3/13.0
12 | Cedar Gate | 14 years | Ammonia | E. coli | 11100 | Lagoon | 1971 | 469287 | 2032 | 2020-10-05 | no | yes | NA
13 | Brookfield Estates | 15 years | Ammonia | E. coli | 10500 | Recirculating sand filter | 2001 | 1307050 | 2033 | 2020-10-05 | no | yes | 3.2/3.2
14 | Quarter Mile Hills | 17 years | Ammonia | E. coli | 5480 | Lagoon | 2001 | 102344 | 2036 | 2020-10-05 | no | yes | 1.9/3.2
15 | Kinkade Crossing | NA |  |  | 50000 | Extended aeration WWTP | 2007 | 381400 | 2034 | 2020-10-05 | yes | no | NA
16 | Meadow Village | NA |  |  | 16500 | Extended aeration WWTP | 2009 | 620000 | 2031 | 2020-10-05 | no | no | NA
17 | Midway Crossing | NA |  |  | 150000 | Extended aeration WWTP | 2008 | 2225518 | 2023 | 2020-10-05 | yes | yes | NA
18 | Prairie Meadows | NA |  |  | 80000 | Extended aeration WWTP | 2004 - 2006 | 3057000 | 2028 | 2020-10-05 | yes | no | NA
[7 empty] | TOTAL: | 20048357
* Brown Station / Richardson Acres combined cost estimate is $1,518,000
** Cost estimates from "User Rate Study 2019 Schedule of Capital Improvement Plan to 2036"
American Outdoor Brands permit expiration: 2023
Eagle Knoll permit expiration: 2023

## By approx. year of construction
| Proposed Permit | Schedule of compliance | Parameter | Parameter | Design Flow | Type of treatment | Approximate year of construction
1 | Highfield Acres | 2025-11-01 | Ammonia | E. coli | 29000 | Lagoon | 1968
2 | Rollingwood | 2025-11-01 | Ammonia | E. coli | 10000 | Extended aeration WWTP | 1968
3 | South Route K | 9 years | Ammonia | E. coli | 244000 | Extended air WWTP / Lagoon | 2000 / 1969
4 | Lee Heights | 2021-11-01 | Ammonia | E. coli | 5000 | Lagoon | 1970
5 | Trails West | 11 years | Ammonia | E. coli | 57500 | Lagoon | 1970
6 | Cedar Gate | 14 years | Ammonia | E. coli | 11100 | Lagoon | 1971
7 | Sunnyslope | 4 years | Ammonia | E. coli | 5500 | Lagoon | 1971
8 | Twin Lakes | 12 years | Ammonia |  | 19400 | Lagoon | 1972
9 | Rocheport | Not applicable |  |  | 34400 | Oxidation ditch WWTP | 1980
10 | Richardson Acres | 2025-11-01 | Ammonia | E. coli | 8510 | Lagoon | 1989
11 | Oberlin Valley | 2021-11-01 | Ammonia | E. coli | 25000 | Extended aeration WWTP | 1998
12 | Brookfield Estates | 15 years | Ammonia | E. coli | 10500 | Recirculating sand filter | 2001
13 | Quarter Mile Hills | 17 years | Ammonia | E. coli | 5480 | Lagoon | 2001
14 | Prairie Meadows | Not applicable |  |  | 80000 | Extended aeration WWTP | 2004 - 2006
15 | Kinkade Crossing | Not applicable |  |  | 50000 | Extended aeration WWTP | 2007
16 | Midway Crossing | Not applicable |  |  | 150000 | Extended aeration WWTP | 2008
17 | Brown Station | 2025-11-01 | Lower ammonia | E. coli | 1850 | Recirculating sand filter | 2009
18 | Meadow Village | Not applicable |  |  | 16500 | Extended aeration WWTP | 2009
19 | Midway Arms | 2024-09-01 | Ammonia |  | 4800 | Recirculating sand filter | 2009
20 | Rocky Fork | 1 year | Ammonia |  | 460000 | Oxidation ditch WWTP | 2013

## By alphabetical order
| Proposed Permit | Schedule of compliance | Parameter | Parameter | Design Flow | Type of treatment | Approximate year of construction
1 | Brookfield Estates | 15 years | Ammonia | E. coli | 10500 | Recirculating sand filter | 2001
2 | Brown Station | 2025-11-01 | Lower ammonia | E. coli | 1850 | Recirculating sand filter | 2009
3 | Cedar Gate | 14 years | Ammonia | E. coli | 11100 | Lagoon | 1971
4 | Highfield Acres | 2025-11-01 | Ammonia | E. coli | 29000 | Lagoon | 1968
5 | Kinkade Crossing | Not applicable |  |  | 50000 | Extended aeration WWTP | 2007
6 | Lee Heights | 2021-11-01 | Ammonia | E. coli | 5000 | Lagoon | 1970
7 | Meadow Village | Not applicable |  |  | 16500 | Extended aeration WWTP | 2009
8 | Midway Arms | 2024-09-01 | Ammonia |  | 4800 | Recirculating sand filter | 2009
9 | Midway Crossing | Not applicable |  |  | 150000 | Extended aeration WWTP | 2008
10 | Oberlin Valley | 2021-11-01 | Ammonia | E. coli | 25000 | Extended aeration WWTP | 1998
11 | Prairie Meadows | Not applicable |  |  | 80000 | Extended aeration WWTP | 2004 - 2006
12 | Quarter Mile Hills | 17 years | Ammonia | E. coli | 5480 | Lagoon | 2001
13 | Richardson Acres | 2025-11-01 | Ammonia | E. coli | 8510 | Lagoon | 1989
14 | Rocheport | 1 year | Ammonia |  | 34400 | Oxidation ditch WWTP | 1980
15 | Rocky Fork | 1 year | Ammonia |  | 460000 | Oxidation ditch WWTP | 2013
16 | Rollingwood | 2025-11-01 | Ammonia | E. coli | 10000 | Extended aeration WWTP | 1968
17 | Sunnyslope | 4 years | Ammonia | E. coli | 5500 | Lagoon | 1971
18 | Trails West | 11 years | Ammonia | E. coli | 57500 | Lagoon | 1970
19 | Twin Lakes | 12 years | Ammonia |  | 19400 | Lagoon | 1972
20 | South Route K | 9 years | Ammonia | E. coli | 244000 | Extended air WWTP / Lagoon | 2000 / 1969